## Sheet1
"Vidarbha Nidhi Hospital" Defect Report
Sr.No | DEFECT_ID | DEFECT_DESCRIPTION | PANEL | MODULE | STEPS TO REPRODUCE | TEST DATA/SOURCE | PRIORITY | SEVERITY | RAISED DATE | ASSIGNED TO | STATUS (CLOSED/OPEN/RUNNING) | CLOSED DATE | COMMENTS from development team | COMMENTS from testing team
1 | DEF_VSNL_001 | Special characters other than alphanumeric, dots and underscores are incorrectly allowed in email field. | Admin | Create Hospital | 1.After login. 2.Click on admin section. 3.Go to create hospital. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | Medium | High | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | Now solved- only gmail allow and not allow email start with number | Done
2 | DEF_VSNL_002 | Email addresses containing consecutive dots are not being rejected. | Admin | Create Hospital | 1.After login. 2.Click on admin section. 3.Go to create hospital. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | Medium | High | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | Now solved-not allow if not valid email format | Done
3 | DEF_VSNL_003 | Emails starting or ending with non-alphanumeric characters are incorrectly accepted. | Admin | Create Hospital | 1.After login. 2.Click on admin section. 3.Go to create hospital. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | Medium | High | 2025-03-26 | 2025-03-26 | Reopened | 2025-04-09 | Now solved start from number and only number not allow in email. | Email allows special characters at the beginning of the address.
4 | DEF_VSNL_004 | The system should accept only 10-digit numeric phone numbers and reject any input with less digits. | Admin | Create Hospital | 1.After login. 2.Click on admin section. 3.Go to create hospital. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | High | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | Now solved | Done
5 | DEF_VSNL_005 | Special characters other than alphanumeric, dots and underscores are incorrectly allowed in email field. | Admin | Pharmacy Registration | 1.After login. 2.Click on admin section. 3.Go to pharmacy registration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | Low | Medium | 2025-03-26 | 2025-03-26 | Open | 2025-04-09 | Now solved. | Done
6 | DEF_VSNL_006 | The system should accept only 10-digit numeric phone numbers and reject any input with less digits. | Admin | Pharmacy Registration | 1.After login. 2.Click on admin section. 3.Go to pharmacy registration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | High | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | Now solved. | Done
7 | DEF_VSNL_007 | Special characters other than alphanumeric, dots and underscores are incorrectly allowed. | Admin | Customer Registeration | 1.After login. 2.Click on admin section. 3.Go to customer registeration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | Medium | High | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | Now solved. | Done
8 | DEF_VSNL_008 | The email validation is not implemented correctly, allowing invalid email formats to be submitted. | Admin | Customer Registeration | 1.After login. 2.Click on admin section. 3.Go to customer registeration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | Medium | High | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | Now solved. | Done
9 | DEF_VSNL_009 | The mobile number field does not enforce the required 10-digit length validation. Users can enter a mobile number with fewer digits, and the form still gets submitted successfully. | Admin | Customer Registeration | 1.After login. 2.Click on admin section. 3.Go to customer registeration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | High | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | Now solved. | Done
10 | DEF_VSNL_010 | The Personal Identification Proof field is marked as mandatory, but the form allows submission without any entry in this field. | Admin | Customer Registeration | 1.After login. 2.Click on admin section. 3.Go to customer registeration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | High | 2025-03-26 | 2025-03-26 | Reopened | 2025-04-09 | Now solved. | Aadhaar number input field is currently accepting any numerical value.There is no validation to check for the required format (12 digits).
11 | DEF_VSNL_011 | Pan detail field is marked as mandatory, but the form allows submission without any entry in this field. | Admin | Customer Registeration | 1.After login. 2.Click on admin section. 3.Go to customer registeration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | Medium | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | Now Solved | Done
12 | DEF_VSNL_012 | The House Tax Details field inside the Address Proof section is marked as mandatory, but the form allows submission without entering any data in this field. | Admin | Customer Registeration | 1.After login. 2.Click on admin section. 3.Go to customer registeration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | Medium | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | Now solved. | Done
13 | DEF_VSNL_013 | The Electric Bill Details field inside the Address Proof section is marked as mandatory, but the form allows submission without entering any data in this field. | Admin | Customer Registeration | 1.After login. 2.Click on admin section. 3.Go to customer registeration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | High | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | Now solved. | Done
14 | DEF_VSNL_014 | The email validation is not implemented correctly, allowing invalid email formats to be submitted. | Admin | Create Doctor | 1.After login. 2.Click on admin section. 3.Go to create doctor. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | Medium | High | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | Now solved. | Done
15 | DEF_VSNL_015 | The mobile number field does not enforce the required 10-digit length validation. Users can enter a mobile number with fewer digits, and the form still gets submitted successfully. | Admin | Create Doctor | 1.After login. 2.Click on admin section. 3.Go to create doctor. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | High | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | Now solved. | Done
16 | DEF_VSNL_016 | The hospital field is marked as mandatory, but the form allows submission without any entry in this field. | Admin | Create Doctor | 1.After login. 2.Click on admin section. 3.Go to create doctor. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | Low | 2025-03-26 | 2025-03-26 | Closed | 09/04/0202 | Now Solved. | Done
17 | DEF_VSNL_017 | Inside doctors list,profile photo is not visible in profile image section. | Admin | Doctors List | 1.After login. 2.Click on admin section. 3.Go to doctors list. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | Low | High | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | It not issue image not show because the data push from localhost and we not push image data on server that's why image not visible on UAT server | Done
18 | DEF_VSNL_018 | The email validation is not implemented correctly, allowing invalid email formats to be submitted. | Admin | Member Registration | 1.After login. 2.Click on admin section. 3.Go to member registration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | Medium | High | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | Now solved. | Done
19 | DEF_VSNL_019 | The mobile number field does not enforce the required 10-digit length validation. Users can enter a mobile number with fewer digits, and the form still gets submitted successfully. | Admin | Member Registration | 1.After login. 2.Click on admin section. 3.Go to member registration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | High | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | Now Solved. | Done
20 | DEF_VSNL_020 | The Submit button remains unclickable if the Hospital field is not selected, but no validation message is displayed. | Admin | Create Scheme | 1.After login. 2.Click on admin section. 3.Go to create scheme. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | Low | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | Now Solved. | Done
21 | DEF_VSNL_021 | Select scheme must be written as enter scheme in create scheme section. | Admin | Create Scheme | 1.After login. 2.Click on admin section. 3.Go to create scheme. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | Low | High | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | Now Solved.This field in input field but mistakenly in show select scheme. | Done
22 | DEF_VSNL_022 | The logo is visible in the Dashboard section, but it is not displayed in other sections. | Admin | Main | 1.After login. 2.Click on admin section. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | High | 2025-03-26 | 2025-03-26 | Closed | 2025-04-09 | Now Solved. | Done
23 | DEF_VSNL_023 | Hospital registration form fails to accept mobile numbers starting with 6. | Admin | Create Hospital | 1.After login. 2.Click on admin section. 3.Go to create hospital. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | High | 2025-04-08 | 2025-04-08 | Closed | 2025-04-09 | solve now allow from number 6 | Done
24 | DEF_VSNL_024 | Pharmacy registration form fails to accept mobile numbers starting with 6. | Admin | Pharmacy Registration | 1.After login. 2.Click on admin section. 3.Go to pharmacy registration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | High | 2025-04-08 | 2025-04-08 | Closed | 2025-04-09 | solve now allow from number 6 | Done
25 | DEF_VSNL_025 | Pathology registration form fails to accept mobile numbers starting with 6. | Admin | Pathology Registeration | 1.After login. 2.Click on admin section. 3.Go to pathology registration.. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | High | 2025-04-08 | 2025-04-08 | Closed | 2025-04-09 | solve now allow from number 6 | Done
26 | DEF_VSNL_026 | Customer register form fails to accept mobile numbers starting with 6. | Admin | Customer Registeration | 1.After login. 2.Click on admin section. 3.Go to customer registration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | High | 2025-04-08 | 2025-04-08 | Closed | 2025-04-09 | solve now allow from number 6 | Done
27 | DEF_VSNL_027 | In customer registration form, the Personal Identification Proof field is marked as mandatory but the form gets submitted successfully without filling in the Personal Identification Proof. | Admin | Customer Registeration | 1.After login. 2.Click on admin section. 3.Go to customer registration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | High | 2025-04-08 | 2025-04-08 | Closed | 2025-04-09 | Now Solved. | Done
28 | DEF_VSNL_028 | In Edit Customer Information ,form submission is blocked and an error message is shown, indicating the email is required—even when it should be optional. | Admin | Customer Registeration | 1.After login. 2.Click on admin section. 3.Go to customer registration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | High | 2025-04-08 | 2025-04-08 | Closed | 2025-04-09 | Now solved. | Done
29 | DEF_VSNL_029 | In Edit Customer Information,Personal Identification Proof is marked as mandatory but the form gets submitted successfully without filling in the Personal Identification Proof. | Admin | Customer Registeration | 1.After login. 2.Click on admin section. 3.Go to customer registration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | Low | Low | 2025-04-08 | 2025-04-08 | Closed | 2025-04-09 | Now solved. | Done
30 | DEF_VSNL_030 | In Edit Customer Information,House Tax Details is marked as mandatory but the form gets submitted successfully without filling in the Personal Identification Proof. | Admin | Customer Registeration | 1.After login. 2.Click on admin section. 3.Go to customer registration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | High | High | 2025-04-08 | 2025-04-08 | Closed | 2025-04-09 | Now solved. | Done
31 | DEF_VSNL_031 | In Edit Customer Information,no validations are shown for any field. | Admin | Customer Registeration | 1.After login. 2.Click on admin section. 3.Go to customer registration. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | Low | Low | 2025-04-08 | 2025-04-08 | Reopened | 2025-04-09 | Now solved. | Not Fixed
32 | DEF_VSNL_032 | Doctor Name and Doctor Email fields are mandatory but do not show the * sign. | Admin | Create Doctor | 1.After login. 2.Click on admin section. 3.Go to create doctor. | http://103.196.193.18/vidarbha_nidhi_health_app/add-hospital/view | Low | Low | 2025-04-08 | 2025-04-08 | Closed | 2025-04-09 | Now solved. | Done

## Sheet2
"Super Pay" Defect Report
Sr.No | DEFECT_ID | DEFECT_DESCRIPTION | PANEL | MODULE | STEPS TO REPRODUCE | TEST DATA/SOURCE | PRIORITY | SEVERITY | STATUS | ASSIGNED TO | CLOSED DATE | COMMENTS from development team | COMMENTS from testing team
1 | DEF_SUPER_PAY_001 | If the number is invalid or contains a country code, an error message is shown. | Dealer | Loan | 1.After login. 2.Click on dealer section. 3.Go to the loan section. 4.Go to create new loan. | http://103.196.193.18/super_pay/dealer/loan/create | Low | High | open | 2025-03-24
2 | DEF_SUPER_PAY_002 | When navigate to aadhar number submit button should disable from PAN card field and not clickable again. | Dealer | Loan | 1.After login. 2.Click on dealer section. 3.Go to the loan section. 4.Go to create new loan. | http://103.196.193.18/super_pay/dealer/loan/create | Medium | High | open | 2025-03-24 |  | solved
3 | DEF_SUPER_PAY_003 | Aadhaar number must only contain numbers and cannot have alphabets. | Dealer | Loan | 1.After login. 2.Click on dealer section. 3.Go to the loan section. 4.Go to create new loan. | http://103.196.193.18/super_pay/dealer/loan/create | Medium | High | open | 2025-03-24 |  | It is take only "e" alphabet and its show validation for mobile nad aadhar field.
4 | DEF_SUPER_PAY_004 | If the response from the Aadhaar verification API is delayed, the system may show a timeout error after a set period or provide an option to retry the request. | Dealer | Loan | 1.After login. 2.Click on dealer section. 3.Go to the loan section. 4.Go to create new loan. | http://103.196.193.18/super_pay/dealer/loan/create | Medium | High | open | 2025-03-24 |  | working on it
5 | DEF_SUPER_PAY_005 | The system should not freeze, and it should provide feedback on the status of the request (whether it's successful, pending, or failed). | Dealer | Loan | 1.After login. 2.Click on dealer section. 3.Go to the loan section. 4.Go to create new loan. | http://103.196.193.18/super_pay/dealer/loan/create | High | High | open | 2025-03-24 |  | working on it
6 | DEF_SUPER_PAY_006 | The system should accurately extract and display the correct address details from the Aadhaar response,which is not displayed. | Dealer | Loan | 1.After login. 2.Click on dealer section. 3.Go to the loan section. 4.Go to create new loan. | http://103.196.193.18/super_pay/dealer/loan/create | Low | Low | open | 2025-03-24
7 | DEF_SUPER_PAY_007 | The Salary field should only accept numeric values, but it currently allows any input, including alphabets, special characters, and spaces. | Dealer | Loan | 1.After login. 2.Click on dealer section. 3.Go to the loan section. 4.Go to create new loan. | http://103.196.193.18/super_pay/dealer/loan/create | Low | Low | open | 2025-03-24 |  | solved
8 | DEF_SUPER_PAY_008 | Since the Gender field is not marked as required, the form should be submitted successfully without an error. | Dealer | Loan | 1.After login. 2.Click on dealer section. 3.Go to the loan section. 4.Go to create new loan. | http://103.196.193.18/super_pay/dealer/loan/create | High | Low | open | 2025-03-24 |  | solved
9 | DEF_SUPER_PAY_009 | The system incorrectly accepts email addresses starting with special characters (e.g., !@gmail.com), which violates standard email format rules. | Dealer | Loan | 1.After login. 2.Click on dealer section. 3.Go to the loan section. 4.Go to create new loan. | http://103.196.193.18/super_pay/dealer/loan/create | Low | High | open | 2025-03-24
10 | DEF_SUPER_PAY_010 | In Pending Loan applications,view button is not working properly. | Dealer | Loan | 1.After login. 2.Click on dealer section. 3.Go to the loan section. 4.Go to pending loans. | http://103.196.193.18/super_pay/dealer/loan | High | High | open | 2025-03-24 |  | This is not an issue in local and UAT not have public folder access.But in live server this is working fine
11 | DEF_SUPER_PAY_011 | Select menu for user is a mandatory field, but the form submits successfully without selecting a value. | Admin | Settings | 1.After login. 2.Click on Admin section. 3.Go to settings. 4.Go to create new user. | http://103.196.193.18/super_pay/settings/user-settings/create | High | High | open | 2025-03-24
12 | DEF_SUPER_PAY_012 | Loan category is a mandatory field, but the form submits successfully without selecting a value. | Admin | Settings | 1.After login. 2.Click on Admin section. 3.Go to settings. 4.Go to sub category master. | http://103.196.193.18/super_pay/settings/subcategories/create | High | High | open | 2025-03-24
13 | DEF_SUPER_PAY_013 | Brand name is a mandatory field, but the form submits successfully without selecting a value. | Admin | Settings | 1.After login. 2.Click on Admin section. 3.Go to product settings. 4.Go to create new product. | http://103.196.193.18/super_pay/settings/products | High | High | open | 2025-03-24
14 | DEF_SUPER_PAY_014 | Model name is a mandatory field, but the form submits successfully without selecting a value. | Admin | Settings | 1.After login. 2.Click on Admin section. 3.Go to product settings. 4.Go to create new product. | http://103.196.193.18/super_pay/settings/products | High | High | open | 2025-03-24
15 | DEF_SUPER_PAY_015 | Variant name is a mandatory field, but the form submits successfully without selecting a value. | Admin | Settings | 1.After login. 2.Click on Admin section. 3.Go to product settings. 4.Go to create new product. | http://103.196.193.18/super_pay/settings/products | High | High | open | 2025-03-24
16 | DEF_SUPER_PAY_016 | Loan catagory,Document catagory and Document status all are required but not mention * sign | Admin | Settings | 1.After login. 2.Click on Admin section. 3.Go to document settings. 4.Go to all required documents. | http://103.196.193.18/super_pay/settings/products | Low | low | open | 2025-03-24
17 | DEF_SUPER_PAY_017 | In Pre-closure settings all fields are required but not mentioned with * sign. | Admin | Settings | 1.After login. 2.Click on Admin section. 3.Go to settings. 4.Go to pre-closure settings. | http://103.196.193.18/super_pay/settings/closures/create | Low | low | open | 2025-03-24
18 | DEF_SUPER_PAY_018 | In city pannel,country code is required but not mentioned with * sign. | Admin | Settings | 1.After login. 2.Click on Admin section. 3.Go to general settings. 4.Go to all city master. | http://103.196.193.18/super_pay/settings/cities/create | Low | low | open | 2025-03-24
19 | DEF_SUPER_PAY_019 | No validation is shown for gender field. | Admin/Approver | Dealer | 1.After login. 2.Click on Admin section. 3.Go to dealer. 4.Go to create new dealer. | http://103.196.193.18/super_pay/agents/dealers/create | High | High | open | 2025-03-24
20 | DEF_SUPER_PAY_020 | Form allows submission without entering Mother's Name, despite the field being marked as mandatory with an asterisk (*). | Admin/Approver | Dealer | 1.After login. 2.Click on Admin section. 3.Go to dealer. 4.Go to create new dealer. | http://103.196.193.18/super_pay/agents/dealers/create | High | High | open | 2025-03-24
21 | DEF_SUPER_PAY_021 | Mobile number field lacks proper validation, allowing numbers to start with invalid digits. | Admin/Approver | Dealer | 1.After login. 2.Click on Admin section. 3.Go to dealer. 4.Go to create new dealer. | http://103.196.193.18/super_pay/agents/dealers/create | High | High | open | 2025-03-24
22 | DEF_SUPER_PAY_022 | Password field accepts any length input despite validation message stating a minimum length of 8 characters. | Admin/Approver | Dealer | 1.After login. 2.Click on Admin section. 3.Go to dealer. 4.Go to create new dealer. | http://103.196.193.18/super_pay/agents/dealers/create | High | High | open | 2025-03-24
23 | DEF_SUPER_PAY_023 | Email field accepts invalid format as email addresses should not start with special characters. | Admin/Approver | Dealer | 1.After login. 2.Click on Admin section. 3.Go to dealer. 4.Go to create new dealer. | http://103.196.193.18/super_pay/agents/dealers/create | High | High | open | 2025-03-24
24 | DEF_SUPER_PAY_024 | View Credit Report not found. | Admin/Approver | Customer | 1.After login. 2.Click on Admin section. 3.Go to customers(Approved loans). 4.Go to loan applicant panel. | http://103.196.193.18/super_pay/customer/approved | Medium | Medium | open | 2025-03-24
25 | DEF_SUPER_PAY_025 | Edit page is not properly visible. | Admin | Customer | 1.After login. 2.Click on Admin section. 3.Go to customers. 4.Go to all customer. | http://103.196.193.18/super_pay/customer/customers/19/edit | High | High | open | 2025-03-24 |  | solved
26 | DEF_SUPER_PAY_026 | Email field accepts invalid format as email addresses should not start with special characters. | Admin | Branch | 1.After login. 2.Click on Admin section. 3.Go to Branch. 4.Go to all Branch Create. | http://103.196.193.18/super_pay/branches/create | High | High | open | 2025-03-24
27 | DEF_SUPER_PAY_027 | Bank Payment Detail field shows a required validation error on form submission despite not being marked as mandatory in the UI. | Admin | Transactions | 1.After login. 2.Click on Admin section. 3.Go to Transactions. 4.Go to new installment. | http://103.196.193.18/super_pay/transaction/installments/create | High | High | open | 2025-03-24
28 | DEF_SUPER_PAY_028 | Missing asterisk (*) for required fields: Balance, Customer Name, and Extra Charge. | Admin | Transactions | 1.After login. 2.Click on Admin section. 3.Go to Transactions. 4.Go to new pre closure. | http://103.196.193.18/super_pay/transaction/press/create | Low | Low | open | 2025-03-24
29 | DEF_SUPER_PAY_029 | Spelling of transaction is wrongly spelled in create preclosure. | Admin | Transactions | 1.After login. 2.Click on Admin section. 3.Go to Transactions. 4.Go to new pre closure. | http://103.196.193.18/super_pay/transaction/press/create | Low | Medium | open | 2025-03-24
30 | DEF_SUPER_PAY_030 | Extra Charge field does not accept input or autofill values. | Admin | Transactions | 1.After login. 2.Click on Admin section. 3.Go to Transactions. 4.Go to new pre closure. | http://103.196.193.18/super_pay/transaction/press/create | High | High | open | 2025-03-24
31 | DEF_SUPER_PAY_031 | View all transaction button is unclickable. | Admin | Transactions | 1.After login. 2.Click on Admin section. 3.Go to Transactions. 4.Go to new pre closure. | http://103.196.193.18/super_pay/transaction/press/create | Low | Low | open | 2025-03-24

## Sheet3
"RIMedicare" Defect Report
Sr.No | DEFECT_ID | DEFECT_DESCRIPTION | PANEL | MODULE | STEPS TO REPRODUCE | TEST DATA/SOURCE | PRIORITY | SEVERITY | STATUS | ASSIGNED TO | CLOSED DATE | COMMENTS from development team | COMMENTS from testing team
1 | DEF_RIMEDICARE_001 | Special characters other than alphanumeric, dots and underscores are incorrectly allowed. | Hospital | Loan Registration | 1.After login. 2.Click on Dealer. 3.Go to settings. 4.Go to loans. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | HIgh | HIgh | Open | 2025-04-07
2 | DEF_RIMEDICARE_002 | Emails starting or ending with non-alphanumeric characters are incorrectly accepted. | Hospital | Loan Registration | 1.After login. 2.Click on Dealer. 3.Go to settings. 4.Go to loans. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | HIgh | HIgh | Open | 2025-04-07
3 | DEF_RIMEDICARE_003 | Login fees should be numeric. | Hospital | Create new loan | 1.After login. 2.Click on Dealer. 3.Go to settings. 4.Go to loans. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | HIgh | HIgh | Open | 2025-04-07
4 | DEF_RIMEDICARE_004 | Guarantor name should take only alphabets. | Hospital | Create new loan | 1.After login. 2.Click on Dealer. 3.Go to settings. 4.Go to loans. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | Low | Low | Open | 2025-04-07
5 | DEF_RIMEDICARE_005 | Card number must take only numeric values. | Hospital | Create new loan | 1.After login. 2.Click on Dealer. 3.Go to settings. 4.Go to loans. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | HIgh | HIgh | Open | 2025-04-07
6 | DEF_RIMEDICARE_006 | First name,father name and last name should only take alphabets. | Hospital | Create new loan | 1.After login. 2.Click on Dealer. 3.Go to settings. 4.Go to loans. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | Low | Low | Open | 2025-04-07
7 | DEF_RIMEDICARE_007 | Mobile number should be valid,it cannot take repeated numbers. | Hospital | Create new loan | 1.After login. 2.Click on Dealer. 3.Go to settings. 4.Go to loans. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | HIgh | Low | Open | 2025-04-07
8 | DEF_RIMEDICARE_008 | When the user attempts to submit the form without entering the product name,the validation message appears correctly, but the application freezes afterward, preventing further interaction. | Hospital | Mandate Registration | 1.After login. 2.Click on Dealer. 3.Go to mandate section. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | HIgh | HIgh | Open | 2025-04-07
9 | DEF_RIMEDICARE_009 | In cash reciept section spelling of date is incorrect | Hospital | Cash Receipt | 1.After login. 2.Click on Dealer. 3.Go to cash receipt section. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | HIgh | HIgh | Open | 2025-04-07
10 | DEF_RIMEDICARE_010 | In the "Create Cash Receipt" functionality, there is no dropdown available for selecting the Loan ID. | Hospital | Cash Receipt | 1.After login. 2.Click on Dealer. 3.Go to cash receipt section. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | HIgh | HIgh | Open | 2025-04-07
11 | DEF_RIMEDICARE_011 | In the "Create Cash Receipt" screen, the Loan ID field is marked as mandatory. However, the form can be submitted without selecting or entering a Loan ID. | Hospital | Cash Receipt | 1.After login. 2.Click on Dealer. 3.Go to cash receipt section. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | Low | HIgh | Open | 2025-04-07
12 | DEF_RIMEDICARE_012 | Mobile number should be valid,it cannot take starting digit as 5. | Admin | Cash Receipt | 1.After login. 2.Click on Admin. 3.Go to customer section. | http://103.196.193.18/rimedicare_hospy/create_fi/2 | HIgh | HIgh | Open | 2025-04-07
13 | DEF_RIMEDICARE_013 | There is no validation for radio buttons. | Admin | Cash Receipt | 1.After login. 2.Click on Admin. 3.Go to customer section. | http://103.196.193.18/rimedicare_hospy/create_fi/3 | HIgh | HIgh | Open | 2025-04-07
14 | DEF_RIMEDICARE_014 | In Ages of Dependents field,the label suggests multiple comma-separated ages are allowed, but only a single value is accepted. | Admin | Cash Receipt | 1.After login. 2.Click on Admin. 3.Go to customer section. | http://103.196.193.18/rimedicare_hospy/create_fi/4 | HIgh | Low | Open | 2025-04-07
15 | DEF_RIMEDICARE_015 | FI created and view button is not working properly. | Admin | Cash Receipt | 1.After login. 2.Click on Admin. 3.Go to customer section. | http://103.196.193.18/rimedicare_hospy/create_fi/5 | HIgh | HIgh | Open | 2025-04-07
16 | DEF_RIMEDICARE_016 | Inside customer panel in edit option,UI is not proper.Headers are missing. | Admin | Cash Receipt | 1.After login. 2.Click on Admin. 3.Go to customer section. 4.Go to all Customers. | http://103.196.193.18/rimedicare_hospy/create_fi/6 | HIgh | HIgh | Open | 2025-04-07
17 | DEF_RIMEDICARE_017 | The form submits successfully even when the User select field is not filled, despite being marked as mandatory. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to user settings. 4.Go to create new user. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | HIgh | HIgh | Open | 2025-04-07
18 | DEF_RIMEDICARE_018 | Emails starting or ending with non-alphanumeric characters are incorrectly accepted. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to user settings. 4.Go to list of users. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | Medium | Medium | Open | 2025-04-07
19 | DEF_RIMEDICARE_019 | Form submission is allowed without selecting any Loan Category, despite it being marked as a required field. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to loan settings.. 4.Go to Sub Category master. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | Low | Low | Open | 2025-04-07
20 | DEF_RIMEDICARE_020 | The dropdown includes a "Select Hospitals" checkbox, which appears to serve no purpose in the current flow. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to loan settings. 4.Go to Field Investigator Allotment. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | Low | Low | Open | 2025-04-07
21 | DEF_RIMEDICARE_021 | Success message not displayed after Branch Mapping submission. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to loan settings. 4.Go to branch mapping. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | Medium | Medium | Open | 2025-04-07
22 | DEF_RIMEDICARE_022 | Mandatory Fields Missing Asterisk Indicators in Loan catagory,Document catagory and Document status field. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to document settings. 4.Go to all required document. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | Medium | Medium | Open | 2025-04-07
23 | DEF_RIMEDICARE_023 | The Country Code field should accept only numeric values | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to general settings. 4.Go to all country master. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | Medium | Medium | Open | 2025-04-07
24 | DEF_RIMEDICARE_024 | In country pannel,upon submission, the screen goes blank and no feedback is provided. The user is left without confirmation of whether the update was successful. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to general settings. 4.Go to all country master. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | High | High | Open | 2025-04-07
25 | DEF_RIMEDICARE_025 | "Select Country" field shows required validation even though it’s not marked as mandatory. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to general settings. 4.Go to all city master. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | Medium | Medium | Open | 2025-04-07
26 | DEF_RIMEDICARE_026 | The form fails to submit despite all required fields being filled. No confirmation message is shown, and the data is not saved. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to general settings. 4.Go to all city master. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | High | High | Open | 2025-04-07
27 | DEF_RIMEDICARE_027 | Form submission fails and city list not updated after adding new entry. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to general settings. 4.Go to all city master. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | High | High | Open | 2025-04-07
28 | DEF_RIMEDICARE_028 | In state master,upon submission, the screen goes blank and no feedback is provided. The user is left without confirmation of whether the update was successful. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to general settings. 4.Go to all state master. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | High | High | Open | 2025-04-07
29 | DEF_RIMEDICARE_029 | Form submission fails when "Manager Name" field is left blank, even though it's not marked as mandatory. | Admin | Branches | 1.After login. 2.Click on Admin. 3.Go to branches. 4.Go to branch create. | http://103.196.193.18/rimedicare_hospy/branches/create | High | Medium | Open | 2025-04-07
30 | DEF_RIMEDICARE_030 | Manager Name field accepts non-alphabetic characters. | Admin | Branches | 1.After login. 2.Click on Admin. 3.Go to branches. 4.Go to branch create. | http://103.196.193.18/rimedicare_hospy/branches/create | Medium | Medium | Open | 2025-04-07
31 | DEF_RIMEDICARE_031 | Emails starting with non-alphanumeric characters are incorrectly accepted. | Admin | Branches | 1.After login. 2.Click on Admin. 3.Go to branches. 4.Go to branch create. | http://103.196.193.18/rimedicare_hospy/branches/create | Low | Low | Open | 2025-04-07
32 | DEF_RIMEDICARE_032 | In edit branch,Form submission fails when "Manager Name" field is left blank, even though it's not marked as mandatory. | Admin | Branches | 1.After login. 2.Click on Admin. 3.Go to branches. 4.Go to list of branches. | http://103.196.193.18/rimedicare_hospy/branches/create | High | High | Open | 2025-04-07
33 | DEF_RIMEDICARE_033 | There is no validation for gender. | Admin | Hospital | 1.After login. 2.Click on Admin. 3.Go to hospital. 4.Go to create new hospital. | http://103.196.193.18/rimedicare_hospy/agents/dealers/create | High | High | Open | 2025-04-07
35 | DEF_RIMEDICARE_034 | Mobile number starting with '5' is accepted, which is invalid as per Indian mobile number format. | Admin | Hospital | 1.After login. 2.Click on Admin. 3.Go to hospital. 4.Go to create new hospital. | http://103.196.193.18/rimedicare_hospy/agents/dealers/create | High | High | Open | 2025-04-07
36 | DEF_RIMEDICARE_035 | Form submission is allowed without selecting mother name, despite it being marked as a required field. | Admin | Hospital | 1.After login. 2.Click on Admin. 3.Go to hospital. 4.Go to create new hospital. | http://103.196.193.18/rimedicare_hospy/agents/dealers/create | High | High | Open | 2025-04-07
37 | DEF_RIMEDICARE_036 | In Relationship Manager Allotment,the dropdown includes a "Select Hospitals" checkbox, which appears to serve no purpose in the current flow. | Admin | Hospital | 1.After login. 2.Click on Admin. 3.Go to hospital. 4.Go to Relationship Manager Allotment. | http://103.196.193.18/rimedicare_hospy/settings/branch-settings/employee-rm-allocation | Low | Low | Open | 2025-04-07
38 | DEF_RIMEDICARE_037 | In Recovery Team Allotment,the dropdown includes a "Select Hospitals" checkbox, which appears to serve no purpose in the current flow. | Admin | Hospital | 1.After login. 2.Click on Admin. 3.Go to hospital. 4.Go to Recovery Team Allotment. | http://103.196.193.18/rimedicare_hospy/settings/branch-settings/employee-rt-allocation | Low | Low | Open | 2025-04-07
39 | DEF_RIMEDICARE_038 | Mobile number starting with '6' is rejected, even though it is valid. | Admin | Customers | 1.After login. 2.Click on Admin. 3.Go to customers. 4.Go to pending loans. | http://103.196.193.18/rimedicare_hospy/dealer/adhar/authentication/0 | High | High | Open | 2025-04-07