## Sheet1
"RIMedicare" Defect Report
Sr.No | DEFECT_ID | DEFECT_DESCRIPTION | PANEL | MODULE | STEPS TO REPRODUCE | TEST DATA/SOURCE | PRIORITY | SEVERITY | STATUS | ASSIGNED TO | CLOSED DATE | COMMENTS from development team | COMMENTS from testing team
1 | DEF_RIMEDICARE_001 | Special characters other than alphanumeric, dots and underscores are incorrectly allowed. | Hospital | Loan Registration | 1.After login. 2.Click on Dealer. 3.Go to settings. 4.Go to loans. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | HIgh | HIgh | Open | 2025-04-07
2 | DEF_RIMEDICARE_002 | Emails starting or ending with non-alphanumeric characters are incorrectly accepted. | Hospital | Loan Registration | 1.After login. 2.Click on Dealer. 3.Go to settings. 4.Go to loans. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | HIgh | HIgh | Open | 2025-04-07
3 | DEF_RIMEDICARE_003 | Login fees should be numeric. | Hospital | Create new loan | 1.After login. 2.Click on Dealer. 3.Go to settings. 4.Go to loans. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | HIgh | HIgh | Open | 2025-04-07
4 | DEF_RIMEDICARE_004 | Guarantor name should take only alphabets. | Hospital | Create new loan | 1.After login. 2.Click on Dealer. 3.Go to settings. 4.Go to loans. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | Low | Low | Open | 2025-04-07
5 | DEF_RIMEDICARE_005 | Card number must take only numeric values. | Hospital | Create new loan | 1.After login. 2.Click on Dealer. 3.Go to settings. 4.Go to loans. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | HIgh | HIgh | Open | 2025-04-07
6 | DEF_RIMEDICARE_006 | First name,father name and last name should only take alphabets. | Hospital | Create new loan | 1.After login. 2.Click on Dealer. 3.Go to settings. 4.Go to loans. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | Low | Low | Open | 2025-04-07
7 | DEF_RIMEDICARE_007 | Mobile number should be valid,it cannot take repeated numbers. | Hospital | Create new loan | 1.After login. 2.Click on Dealer. 3.Go to settings. 4.Go to loans. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | HIgh | Low | Open | 2025-04-07
8 | DEF_RIMEDICARE_008 | When the user attempts to submit the form without entering the product name,the validation message appears correctly, but the application freezes afterward, preventing further interaction. | Hospital | Mandate Registration | 1.After login. 2.Click on Dealer. 3.Go to mandate section. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | HIgh | HIgh | Open | 2025-04-07
9 | DEF_RIMEDICARE_009 | In cash reciept section spelling of date is incorrect | Hospital | Cash Receipt | 1.After login. 2.Click on Dealer. 3.Go to cash receipt section. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | HIgh | HIgh | Open | 2025-04-07
10 | DEF_RIMEDICARE_010 | In the "Create Cash Receipt" functionality, there is no dropdown available for selecting the Loan ID. | Hospital | Cash Receipt | 1.After login. 2.Click on Dealer. 3.Go to cash receipt section. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | HIgh | HIgh | Open | 2025-04-07
11 | DEF_RIMEDICARE_011 | In the "Create Cash Receipt" screen, the Loan ID field is marked as mandatory. However, the form can be submitted without selecting or entering a Loan ID. | Hospital | Cash Receipt | 1.After login. 2.Click on Dealer. 3.Go to cash receipt section. | http://103.196.193.18/rimedicare_hospy/dealer/loan/create | Low | HIgh | Open | 2025-04-07
12 | DEF_RIMEDICARE_012 | Mobile number should be valid,it cannot take starting digit as 5. | Admin | Cash Receipt | 1.After login. 2.Click on Admin. 3.Go to customer section. | http://103.196.193.18/rimedicare_hospy/create_fi/2 | HIgh | HIgh | Open | 2025-04-07
13 | DEF_RIMEDICARE_013 | There is no validation for radio buttons. | Admin | Cash Receipt | 1.After login. 2.Click on Admin. 3.Go to customer section. | http://103.196.193.18/rimedicare_hospy/create_fi/3 | HIgh | HIgh | Open | 2025-04-07
14 | DEF_RIMEDICARE_014 | In Ages of Dependents field,the label suggests multiple comma-separated ages are allowed, but only a single value is accepted. | Admin | Cash Receipt | 1.After login. 2.Click on Admin. 3.Go to customer section. | http://103.196.193.18/rimedicare_hospy/create_fi/4 | HIgh | Low | Open | 2025-04-07
15 | DEF_RIMEDICARE_015 | FI created and view button is not working properly. | Admin | Cash Receipt | 1.After login. 2.Click on Admin. 3.Go to customer section. | http://103.196.193.18/rimedicare_hospy/create_fi/5 | HIgh | HIgh | Open | 2025-04-07
16 | DEF_RIMEDICARE_016 | Inside customer panel in edit option,UI is not proper.Headers are missing. | Admin | Cash Receipt | 1.After login. 2.Click on Admin. 3.Go to customer section. 4.Go to all Customers. | http://103.196.193.18/rimedicare_hospy/create_fi/6 | HIgh | HIgh | Open | 2025-04-07
17 | DEF_RIMEDICARE_017 | The form submits successfully even when the User select field is not filled, despite being marked as mandatory. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to user settings. 4.Go to create new user. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | HIgh | HIgh | Open | 2025-04-07
18 | DEF_RIMEDICARE_018 | Emails starting or ending with non-alphanumeric characters are incorrectly accepted. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to user settings. 4.Go to list of users. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | Medium | Medium | Open | 2025-04-07
19 | DEF_RIMEDICARE_019 | Form submission is allowed without selecting any Loan Category, despite it being marked as a required field. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to loan settings.. 4.Go to Sub Category master. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | Low | Low | Open | 2025-04-07
20 | DEF_RIMEDICARE_020 | The dropdown includes a "Select Hospitals" checkbox, which appears to serve no purpose in the current flow. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to loan settings. 4.Go to Field Investigator Allotment. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | Low | Low | Open | 2025-04-07
21 | DEF_RIMEDICARE_021 | Success message not displayed after Branch Mapping submission. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to loan settings. 4.Go to branch mapping. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | Medium | Medium | Open | 2025-04-07
22 | DEF_RIMEDICARE_022 | Mandatory Fields Missing Asterisk Indicators in Loan catagory,Document catagory and Document status field. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to document settings. 4.Go to all required document. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | Medium | Medium | Open | 2025-04-07
23 | DEF_RIMEDICARE_023 | The Country Code field should accept only numeric values | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to general settings. 4.Go to all country master. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | Medium | Medium | Open | 2025-04-07
24 | DEF_RIMEDICARE_024 | In country pannel,upon submission, the screen goes blank and no feedback is provided. The user is left without confirmation of whether the update was successful. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to general settings. 4.Go to all country master. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | High | High | Open | 2025-04-07
25 | DEF_RIMEDICARE_025 | "Select Country" field shows required validation even though it’s not marked as mandatory. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to general settings. 4.Go to all city master. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | Medium | Medium | Open | 2025-04-07
26 | DEF_RIMEDICARE_026 | The form fails to submit despite all required fields being filled. No confirmation message is shown, and the data is not saved. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to general settings. 4.Go to all city master. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | High | High | Open | 2025-04-07
27 | DEF_RIMEDICARE_027 | Form submission fails and city list not updated after adding new entry. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to general settings. 4.Go to all city master. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | High | High | Open | 2025-04-07
28 | DEF_RIMEDICARE_028 | In state master,upon submission, the screen goes blank and no feedback is provided. The user is left without confirmation of whether the update was successful. | Admin | Settings | 1.After login. 2.Click on Admin. 3.Go to general settings. 4.Go to all state master. | http://103.196.193.18/rimedicare_hospy/settings/companies/create | High | High | Open | 2025-04-07
29 | DEF_RIMEDICARE_029 | Form submission fails when "Manager Name" field is left blank, even though it's not marked as mandatory. | Admin | Branches | 1.After login. 2.Click on Admin. 3.Go to branches. 4.Go to branch create. | http://103.196.193.18/rimedicare_hospy/branches/create | High | Medium | Open | 2025-04-07
30 | DEF_RIMEDICARE_030 | Manager Name field accepts non-alphabetic characters. | Admin | Branches | 1.After login. 2.Click on Admin. 3.Go to branches. 4.Go to branch create. | http://103.196.193.18/rimedicare_hospy/branches/create | Medium | Medium | Open | 2025-04-07
31 | DEF_RIMEDICARE_031 | Emails starting with non-alphanumeric characters are incorrectly accepted. | Admin | Branches | 1.After login. 2.Click on Admin. 3.Go to branches. 4.Go to branch create. | http://103.196.193.18/rimedicare_hospy/branches/create | Low | Low | Open | 2025-04-07
32 | DEF_RIMEDICARE_032 | In edit branch,Form submission fails when "Manager Name" field is left blank, even though it's not marked as mandatory. | Admin | Branches | 1.After login. 2.Click on Admin. 3.Go to branches. 4.Go to list of branches. | http://103.196.193.18/rimedicare_hospy/branches/create | High | High | Open | 2025-04-07
33 | DEF_RIMEDICARE_033 | There is no validation for gender. | Admin | Hospital | 1.After login. 2.Click on Admin. 3.Go to hospital. 4.Go to create new hospital. | http://103.196.193.18/rimedicare_hospy/agents/dealers/create | High | High | Open | 2025-04-07
35 | DEF_RIMEDICARE_034 | Mobile number starting with '5' is accepted, which is invalid as per Indian mobile number format. | Admin | Hospital | 1.After login. 2.Click on Admin. 3.Go to hospital. 4.Go to create new hospital. | http://103.196.193.18/rimedicare_hospy/agents/dealers/create | High | High | Open | 2025-04-07
36 | DEF_RIMEDICARE_035 | Form submission is allowed without selecting mother name, despite it being marked as a required field. | Admin | Hospital | 1.After login. 2.Click on Admin. 3.Go to hospital. 4.Go to create new hospital. | http://103.196.193.18/rimedicare_hospy/agents/dealers/create | High | High | Open | 2025-04-07
37 | DEF_RIMEDICARE_036 | In Relationship Manager Allotment,the dropdown includes a "Select Hospitals" checkbox, which appears to serve no purpose in the current flow. | Admin | Hospital | 1.After login. 2.Click on Admin. 3.Go to hospital. 4.Go to Relationship Manager Allotment. | http://103.196.193.18/rimedicare_hospy/settings/branch-settings/employee-rm-allocation | Low | Low | Open | 2025-04-07
38 | DEF_RIMEDICARE_037 | In Recovery Team Allotment,the dropdown includes a "Select Hospitals" checkbox, which appears to serve no purpose in the current flow. | Admin | Hospital | 1.After login. 2.Click on Admin. 3.Go to hospital. 4.Go to Recovery Team Allotment. | http://103.196.193.18/rimedicare_hospy/settings/branch-settings/employee-rt-allocation | Low | Low | Open | 2025-04-07
39 | DEF_RIMEDICARE_038 | Mobile number starting with '6' is rejected, even though it is valid. | Admin | Customers | 1.After login. 2.Click on Admin. 3.Go to customers. 4.Go to pending loans. | http://103.196.193.18/rimedicare_hospy/dealer/adhar/authentication/0 | High | High | Open | 2025-04-07